## Log
Team Name: | Group 2
Topic: | MediPath |  |  |  | Meeting minutes in log
Contributions to source code
Team Members |  |  |  |  | Finish algorithm
Members | Role(s) |  |  |  | Testing
Alex Kingsland | Google Maps API |  |  |  | Big decision (swing vs website, algorithm choice)
Artem Kokhanov | Displaying Results |  |  |  | Submitting document
Eoin Lynagh | Narrowing Query |  |  |  | 7/week
Graeme Woods | Database Hosting
Moziah San Vicente | Database Sorting and Analyzing
TimeStamp YYMMDDThh:mm | Originator | Type | Task ID | Status | Comments | Supporting Documents
180207T14:30 | All | Meeting | 1 | Completed | Project Plan Meeting | 2XB3_FinalProjectMeeting_1.docx
180207T16:30 | All | Submission | 2 | Initialized | Project Topic Decided, Objectives Discussed, Roles Assigned | Group02ProjectPlan.docx
180207T17:00 | All | Submission | 2 | Completed | Project Plan | Group02ProjectPlan.docx
180216T16:30 | All | Submission | 2 | Completed | Project Topic Decided, Objectives Discussed, Roles Assigned | Group02ProjectPlan.docx
180224T12:00 | All | Meeting | 3 | Completed | Requirements Meeting | 2XB3_FinalProjectMeeting_2.docx
180225T09:00 | Moziah San Vicente | Submission | 4 | Completed | Functional Requirements | Requirement_Specification.pdf
180225T11:00 | Graeme Woods | Submission | 4 | Completed | Non-Functional Requirements | Requirement_Specification.pdf
180225T14:00 | Artem Kokhanov | Submission | 4 | Completed | Requirements on the Development and Maintenance Process | Requirement_Specification.pdf
180225T18:30 | Alex Kingsland | Submission | 4 | Completed | Domain | Requirement_Specification.pdf
180303T21:00 | All | Decision | 5 | Completed | Organize Github Meeting
180305T16:00 | All | Meeting | 6 | Completed | Github Meeting | 2XB3_FinalProjectMeeting_3.docx
180305T16:00 | Moziah San Vicente | Change | 7 | Completed | Add ReadExcel.java
180305T16:30 | All | Change | 8 | Completed | Creation of Github
180306T16:00 | Eoin Lynagh | Change | 9 | Completed | Add RBbst and hashing to ReadExcel.java
180307T16:00 | Alex & Eoin | Change | 10 | Completed | Connect ReadExcel.java with RBbst and hashing
180308T10:00 | Graeme Woods | Decision | 11 | Completed | Restructure team (Graeme: project log, Eoin: meeting minutes)
180311T21:00 | All | Decision | 12 | Completed | Organize Backend Implementation meeting
180312T16:30 | Graeme Woods | Meeting | 13 | Completed | Meeting with Dr Samavi to get website working
180313T16:00 | All | Meeting | 14 | Completed | Backend Implementation meeting | 2XB3_FinalProjectMeeting_4.docx
180313T16:00 | All | Decision | 15 | Completed | Restructure Roles
180313T16:00 | Graeme Woods | Change | 16 | Completed | Clean up directory
180313T16:30 | Alex Kingsland | Change | 17 | Completed | Add Distance.java
180313T17:00 | Eoin & Moziah | Change | 18 | Completed | Connect Distance.java to hashing and ReadExcel.java
180315T09:00 | Graeme Woods | Change | 19 | Completed | POC of surgery selector website working
180315T09:30 | Alex & Eoin | Change | 20 | Completed | Added Client Code
180320T14:30 | All | Meeting |  | completed
180320T09:31 | Moziah San Vicente |  | 21 | Started | Structure for Website layout(Design/Drawing)
180320T09:32 | Artem Kokhanov |  | 22 | Started | Logo Designs
180320T09:33 | Graeme Woods |  | 23 | Completed | Front page of Website
180320T09:35 | All | Decision | 22 | Completed | Decided on Logo Design
180320T09:35 | Alex & Eoin | Change | 26 | Started | Graph implementation for our program
180325T19:00 | All | Meeting |  | completed
180327T09:36 | Moziah San Vicente |  | 27 | Started | Slides
180329T09:37 | Artem Kokhanov |  | 28 | Completed | Slides
180330T09:38 | Graeme Woods |  |  | Started | Implementing the website through tomcat with our java code
180330T09:38 | Moziah San Vicente |  | 29 | Completed | Dropdown menu for procedure List on website
180331T14:30 | Moziah San Vicente | Change | 32 | Completed | error found and corrected in the readecel file
180401T14:30 | Alex | Change | 33 | Completed | Graph implementation and methods
180402T14:31 | All | Meeting |  | Completed