## Log
Team Name: | Group 2
Topic: | MediPath |  |  |  | Meeting minutes in log
Contributions to source code
Team Members |  |  |  |  | Finish algorithm
Members | Role(s) |  |  |  | Testing
Alex Kingsland | Google Maps API |  |  |  | Big decision (swing vs website, algorithm choice)
Artem Kokhanov | Displaying Results |  |  |  | Submitting document
Eoin Lynagh | Narrowing Query |  |  |  | 7/week
Graeme Woods | Database Hosting
Moziah San Vicente | Database Sorting and Analyzing
TimeStamp YYMMDDThh:mm | Originator | Type | Task ID | Status | Comments | Supporting Documents
180207T14:30 | All | Meeting |  | Completed | Project Plan Meeting | 2XB3_FinalProjectMeeting_1.docx
180207T16:30 | All | Submission |  | Initialized | Project Topic Decided, Objectives Discussed, Roles Assigned | Group02ProjectPlan.docx
180207T17:00 | All | Submission |  | Completed | Project Plan | Group02ProjectPlan.docx
180216T16:30 | All | Submission |  | Completed | Project Topic Decided, Objectives Discussed, Roles Assigned | Group02ProjectPlan.docx
180224T12:00 | All | Meeting |  | Completed | Requirements Meeting | 2XB3_FinalProjectMeeting_2.docx
180225T09:00 | Moziah San Vicente | Submission |  | Completed | Functional Requirements | Requirement_Specification.pdf
180225T11:00 | Graeme Woods | Submission |  | Completed | Non-Functional Requirements | Requirement_Specification.pdf
180225T14:00 | Artem Kokhanov | Submission |  | Completed | Requirements on the Development and Maintenance Process | Requirement_Specification.pdf
180225T18:30 | Alex Kingsland | Submission |  | Completed | Domain | Requirement_Specification.pdf
180303T21:00 | All | Decision |  | Completed | Organize Github Meeting
180305T4:00 | All | Meeting |  | Completed | Github Meeting | 2XB3_FinalProjectMeeting_3.docx
180305T4:00 | Moziah San Vicente | Change |  | Completed | Add ReadExcel.java
180306T4:00 | Eoin Lynagh | Change |  | Completed | Add RBbst and hashing to ReadExcel.java
180308T10:00 | Graeme Woods | Decision |  | Completed | Restructure team (Graeme: project log, Eoin: meeting minutes)
180311T21:00 | All | Decision |  | Completed | Organize Backend Implementation meeting
180313T04:00 | All | Meeting |  | Completed | Backend Implementation meeting | 2XB3_FinalProjectMeeting_4.docx
180313T04:00 | All | Decision |  | Completed | restructure roles
180313T04:00 | Graeme Woods | Change |  | Completed | Clean up directory
180313T04:30 | Alex Kingsland | Change |  | Completed | Add Distance.java